## Sheet1
ID | Risk Description | Category | Likelihood | Impact | Risk Level | Phase | Mitigation Strategy
R1 | Inaccurate location data for evacuation routes | Technical | Medium | High | High | Initial Planning | Use verified mapping APIs (e.g., Google Maps, Mapbox) and allow user correction
R2 | Chatbot gives outdated or incorrect advice | Functional | Low | High | Medium | Development | Regularly update AI models and integrate with real-time verified sources
R3 | App unavailable during an actual emergency | Technical | Medium | High | High | Deployment | Enable offline storage of plans and downloadable PDFs
R4 | Users don’t print or save their plans ahead of time | User Behavior | High | Medium | High | Deployment | In-app reminders and notifications to prompt saving/printing
R5 | Privacy concerns with storing user location data | Legal / Security | Medium | High | High | Initial Planning | Use encryption, anonymize data, and add clear privacy policy
R6 | Limited internet access in disaster areas | Environmental | High | High | High | Deployment | Include offline mode and integrate with low-bandwidth fallback systems
R7 | App misunderstood as a substitute for official alerts | Communication | Low | Medium | Medium | Development | Include disclaimers and redirect users to FEMA, local alerts, etc.
R8 | Third-party API dependency failures | Technical | Medium | Medium | Medium | Development | Build fallback logic and monitor API uptime proactively
R9 | Inadequate testing leading to bugs in critical functions | Quality Assurance | Medium | High | High | Testing | Conduct thorough unit and integration testing
R10 | Insufficient user adoption or interest | Business | Medium | High | High | Post-Launch | Launch targeted marketing and outreach campaigns
R11 | Misinterpretation of AI chatbot responses | Functional | Medium | Medium | Medium | Development | Add disclaimers and offer response feedback options
R12 | Device compatibility issues (older phones/tablets) | Technical | Medium | Medium | Medium | Testing | Perform compatibility testing on various devices and OS versions
R13 | Inaccurate or outdated shelter data | Data Integrity | High | High | High | Maintenance | Regularly verify and sync with authoritative shelter databases
R14 | Budget overruns during development | Financial | Medium | High | High | Development | Track expenses closely and maintain a contingency fund
R15 | Team burnout due to tight deadlines | Team Management | Medium | Medium | Medium | Development | Set realistic timelines and encourage work-life balance