## Sheet1
Project Name | Project Manager | Charge Code | Customer | Project Status | Task Name | Planned Start Date | Planned Finish Date | Planned Duration | Planned Hours | Planned Cost | Planned Resource Cost | Percent Complete | Linked From | Linked To | Actual Start Date | Actual Finish Date | Actual Duration | Actual Hours | Actual Cost | Actual Resource Cost | Remaining Hours | Milestone | Complete | Priority | WBS | Locked | Baseline Duration | Baseline Hours | Baseline Start Date | Baseline Finish Date | Baseline Cost | Notes | Summary | Dependency (From) | Dependency (To) | Tags | Board | To Do list
MNat.ai - Group 5 | Calvin Mitchell |  |  | Planning | 1. Project Management(PM) | 2025-02-25 | 2025-04-01 | 25 days | 744 hours | 42665 | 20000 | 0 | [8 empty] | 744 hours | False | False | Medium | 1 | False | [5 empty] | Do stuff here. | True |  |  |  | To Do
MNat.ai - Group 5 | Calvin Mitchell |  |  | Planning | 1.1 Project Initiation and Planning | 2025-02-25 | 2025-03-10 | 10 days | 240 hours | 12075 | 16000 | 0 | [8 empty] | 240 hours | False | False | Medium | 1.1 | False | [5 empty] | Everything you need to describe the task can be listed here | False |  |  | Meeting | Done
MNat.ai - Group 5 | Calvin Mitchell |  |  | Planning | 1.2 Risk Management | 2025-03-10 | 2025-03-19 | 8 days | 192 hours | 5865 | 4000 | 0 | [8 empty] | 192 hours | False | False |  | 1.2 | False | [6 empty] | False |  |  |  | Doing
MNat.ai - Group 5 | Calvin Mitchell |  |  | Planning | 1.3 Stakeholder Communication | 2025-03-20 | 2025-03-31 | 8 days | 192 hours | 13685 |  | 0 |  | 1.4 Project Tracking and Reporting | [6 empty] | 192 hours | False | False | High | 1.3 | False | [6 empty] | False |  |  |  | To Do
MNat.ai - Group 5 | Calvin Mitchell |  |  | Planning | 1.4 Project Tracking and Reporting | 2025-04-01 | 2025-04-01 |  | 120 hours | 11040 |  | 0 | 1.3 Stakeholder Communication | 2.1 Gather Requirements, 3.2 UI/UX Design and Testing | [6 empty] | 120 hours | True | False | Critical | 1.4 | False | [6 empty] | False |  |  |  | To Do
MNat.ai - Group 5 | Calvin Mitchell |  |  | Planning | 2. Requirement Analysis and Planning | 2025-04-01 | 2025-05-06 | 26 days | 624 hours | 50140 |  | 0 | [8 empty] | 624 hours | False | False | Medium | 2 | False | [6 empty] | True |  |  |  | To Do
MNat.ai - Group 5 | Calvin Mitchell |  |  | Planning | 2.1 Gather Requirements | 2025-04-01 | 2025-04-11 | 9 days | 216 hours | 15410 |  | 0 | 1.4 Project Tracking and Reporting | 2.2 Define System Functionalities | [6 empty] | 216 hours | False | False | Medium | 2.1 | False | [6 empty] | False |  |  |  | To Do
MNat.ai - Group 5 | Calvin Mitchell |  |  | Planning | 2.2 Define System Functionalities | 2025-04-14 | 2025-04-23 | 8 days | 192 hours | 17365 |  | 0 | 2.1 Gather Requirements | 2.3 Document Data Storage Needs | [6 empty] | 192 hours | False | False | Medium | 2.2 | False | [6 empty] | False |  |  |  | To Do
MNat.ai - Group 5 | Calvin Mitchell |  |  | Planning | 2.3 Document Data Storage Needs | 2025-04-24 | 2025-05-06 | 9 days | 216 hours | 17365 |  | 0 | 2.2 Define System Functionalities | [7 empty] | 216 hours | True | False | Critical | 2.3 | False | [6 empty] | False |  |  |  | To Do
MNat.ai - Group 5 | Calvin Mitchell |  |  | Planning | 3. System Design and Architeture | 2025-05-14 | 2025-06-23 | 29 days | 816 hours | 64745 |  | 0 | [8 empty] | 816 hours | False | False | Medium | 3 | False | [6 empty] | True |  |  |  | To Do
MNat.ai - Group 5 | Calvin Mitchell |  |  | Planning | 3.1 Database Design and Development | 2025-05-14 | 2025-05-28 | 11 days | 264 hours | 23862.5 |  | 0 | [8 empty] | 264 hours | False | False | Medium | 3.1 | False | [6 empty] | False |  |  | Ticket | To Do
MNat.ai - Group 5 | Calvin Mitchell |  |  | Planning | 3.2 UI/UX Design and Testing | 2025-05-22 | 2025-06-06 | 12 days | 288 hours | 20182.5 |  | 0 | 1.4 Project Tracking and Reporting | 4.2 Testing and Feedback, 3.3 Secure Data Integration | [6 empty] | 288 hours | False | False | Medium | 3.2 | False | [6 empty] | False |  |  |  | To Do
MNat.ai - Group 5 | Calvin Mitchell |  |  | Planning | 3.3 Secure Data Integration | 2025-06-09 | 2025-06-23 | 11 days | 264 hours | 20700 |  | 0 | 3.2 UI/UX Design and Testing | [7 empty] | 264 hours | True | False | Critical | 3.3 | False | [6 empty] | False |  |  |  | To Do
MNat.ai - Group 5 | Calvin Mitchell |  |  | Planning | 4. Development and Implementation | 2025-06-30 | 2025-08-11 | 31 days | 888 hours | 109135 |  | 0 | [8 empty] | 888 hours | False | False | Medium | 4 | False | [6 empty] | True |  |  |  | To Do
MNat.ai - Group 5 | Calvin Mitchell |  |  | Planning | 4.1 Code Development and Prototyping | 2025-06-30 | 2025-07-21 | 16 days | 384 hours | 42435 |  | 0 | [8 empty] | 384 hours | False | False | Medium | 4.1 | False | [6 empty] | False |  |  | Ticket | To Do
MNat.ai - Group 5 | Calvin Mitchell |  |  | Planning | 4.2 Testing and Feedback | 2025-07-14 | 2025-07-29 | 12 days | 288 hours | 33350 |  | 0 | 3.2 UI/UX Design and Testing | 4.3 Final Integration | [6 empty] | 288 hours | False | False | Medium | 4.2 | False | [6 empty] | False |  |  |  | To Do
MNat.ai - Group 5 | Calvin Mitchell |  |  | Planning | 4.3 Final Integration | 2025-07-30 | 2025-08-11 | 9 days | 216 hours | 33350 |  | 0 | 4.2 Testing and Feedback | [7 empty] | 216 hours | True | False | Critical | 4.3 | False | [6 empty] | False |  |  |  | To Do